### CONCLUSION BY THE SECTION

* Total MRs – 94 + 4 additional
* Material Requisitions Issued – 97;
* Request for Quotation Floated – 97;
* Bids Opened – 97;
* Complete Evaluation – 97;
* Purchase Orders Issued – 93 + 4;
* Lot #1, #2 cargo of CGT package offloaded and stored in Korea;
* Barge with LLI items (CGT, Separators, Flare KnockOut Drum) towing from Masan arrived to BLF Site on July;
* Field Auxillary Room Structures - 78 containers (785 Tons) dispatched to site. Bolts will be dispatched from China;
* Steel fabrication in progress.
* Piping items fabrication in progress.
* Inert materials (locally procured) under delivery;
* 10 kV Packaged Substation and Integrated Transformers 2 and 3 under delivery to Novosibirsk

### PROBLEMATIC ISSUES

* Subcontractor slow manufacturing progress. More resources, equipment and people will be allocated. Frequent engagement with Subcontractor at project management level;
* Subcontractor is to provide separate list for quantity in their warehouse and needs to be impact tests, with planned dates;
* Subcontractor failed in Ultrasonic Testing (PAUT) demonstration. Subcontractor considering sourcing/renting proper equipment and staff for ultrasonic testing PAUT.

### PLANS, КEY EVENTS FOR NEXT PERIOD

* Conclude change orders for “Top Up” items;
* Request for Quotation for Air Cooler Heat Exchanger cargo logistics movement finalization;
* LLI offloading to site;